## GanttChart
FSB Project Schedule
Phoenix Team
| Project Start Date | 2021-05-17 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Đào Duy Tùng | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05
 | time axis 2021-05-17 to 2021-07-11
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-05-17 to 2021-07-11
1 | Mở đầu, giới thiệu về dự án |  |  |  | - |  |  | -
1.1 | Phát triển ý tưởng ban đầu của dự án | Tùng |  | 2021-05-17 | 2021-05-18 | 2 | 100% | 2
1.2 | Tổng quan về các giải pháp tương tự hiện có | Giáp |  | 2021-05-19 | 2021-05-20 | 2 | 100% | 2
1.3 | Phác thảo kinh doanh | Minh |  | 2021-05-21 | 2021-05-21 | 1 | 100% | 1
1.4 | Các hạn chế của hệ thống hiện tại | Giáp |  | 2021-05-22 | 2021-05-23 | 2 | 100% | 0
2 | Xây dựng Kế hoạch quản lý dự án phần mềm (SPMP) |  |  |  | - |  |  | -
2.1 | Xác định vấn đề | Tùng |  | 2021-05-24 | 2021-05-24 | 1 | 100% | 1
2.2 | Tổ chức dự án | Giáp |  | 2021-05-25 | 2021-05-26 | 2 | 100% | 2
2.3 | Lập kế hoạch quản lý dự án | Minh |  | 2021-05-27 | 2021-05-30 | 4 | 100% | 2
3 | Xây dựng Đặc tả yêu cầu phần mềm (SRS) |  |  |  | - |  |  | -
3.1 | Mô tả yêu cầu người dùng | Minh |  | 2021-05-31 | 2021-06-03 | 4 | 100% | 4
3.2 | Đặc tả yêu cầu hệ thống (Yêu cầu cụ thể) | Tùng |  | 2021-06-04 | 2021-06-09 | 6 | 100% | 4
3.3 | Sơ đồ mối quan hệ thực thể hoặc cơ sở dữ liệu | Giáp |  | 2021-06-10 | 2021-06-13 | 4 | 100% | 2
4 | Mô tả thiết kế phần mềm (SDD) |  |  |  | - |  |  | -
4.1 | Thiết kế kiến trúc hệ thống |  |  | 2021-06-14 | 2021-06-18 | 5 | 100% | 5
4.2 | Sơ đồ thành phần và mô tả chi tiết của các thành phần |  |  | 2021-06-19 | 2021-06-20 | 2 | 100% | 0
4.3 | Sơ đồ trình tự |  |  | 2021-06-21 | 2021-06-22 | 2 | 100% | 2
4.4 | Thiết kế giao diện người dùng |  |  | 2021-06-23 | 2021-06-25 | 3 | 100% | 3
4.5 | Thiết kế cơ sở dữ liệu |  |  | 2021-06-26 | 2021-06-27 | 2 | 100% | 0
5 | Viết mã nguồn và tích hợp mã nguồn |  |  |  | - |  |  | -
5.1 | Viết mã nguồn chương trình frontend |  |  | 2021-06-28 | 2021-07-07 | 10 | 100% | 8
5.2 | Viết mã nguồn chương trình backend |  |  | 2021-07-08 | 2021-07-15 | 8 | 100% | 6
5.3 | Xem xét lại mã nguồn (review code) |  |  | 2021-07-16 | 2021-07-20 | 5 | 100% | 3
5.4 | Tích hợp mã nguồn chương trình. |  |  | 2021-07-21 | 2021-07-25 | 5 | 100% | 3
6 | Lập hồ sơ kiểm thử phần mềm (STD) |  |  |  | - |  |  | -
6.1 | Thiết kế test case. |  |  | 2021-07-26 | 2021-07-27 | 2 | 100% | 2
6.2 | Tiến hành kiểm thử sản phẩm, báo cáo lại các lỗi |  |  | 2021-07-28 | 2021-07-30 | 3 | 100% | 3
6.3 | Fix bug và đảm bảo các lỗi đều được khắc phục |  |  | 2021-07-31 | 2021-08-01 | 2 | 100% | 0
7 | Hướng dẫn sử dụng phần mềm |  |  |  | - |  |  | -
7.1 | Viết hướng dẫn sử dụng phần mềm. |  |  | 2021-08-02 | 2021-08-02 | 1 | 100% | 1
7.2 | Chuẩn bị điều kiện cần thiết và phần mềm và phần cứng để chạy demo. |  |  | 2021-08-03 | 2021-08-03 | 1 | 100% | 1
8 | Đóng gói và triển khai |  |  |  | - |  |  | -
8.1 | Chạy ứng dụng trên thiết bị local |  |  | 2021-08-04 | 2021-08-05 | 2 | 100% | 2
8.2 | Triển khai ứng dụng lên server |  |  | 2021-08-06 | 2021-08-07 | 2 | 100% | 1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.